## WBS - Sprint
Nama Project : WATI CR
Start Date : 18 Februari 2026
Start Date : 20 April 2026
WBS | SA | TL | BA | SM | UI | DBA | BE1 | BE2 | FE1 | FE2 | QA | DevOps | TW
Sprint 1 (18 Februari - 03 Maret 2026) | 5 | 5 | 5 | 5 | 5 | 8 | 4 | 6 |  |  | 2 | 2 | 2
Requirement Gathering
Requirement Gathering
Design UI/UX
Design Review Meeting
Design Finalization
Development
Midleware
Create service api to access cyberapp (be) - 2 | [6 empty] | 2
Create queue consumer log mapping (be) - 5 | [7 empty] | 5
Create queue consumer blocking soar (be) - 2 | [6 empty] | 2
Create midleware autorization (be) - 1 | [7 empty] | 1
Wati Dashboard
DBA design database - 8 | [5 empty] | 8
Sprint 2 (04- 17 Maret 2026) | 5 | 5 | 5 | 5 | 2 | 2 | 8 | 5 | 7 | 4 | 3 | 2 | 2
Response
Create service api response list (be) - 1 | [6 empty] | 2
Create service api response detail (be) - 1 | [7 empty] | 2
Create service api close (be) -1 | [6 empty] | 2
Create service api re-open (be) - 1 | [7 empty] | 1
Create service api input response (be) - 2 | [6 empty] | 2
Create service api blocking soar (be) - 2 | [7 empty] | 2
Create service api push & get command (be) - 2 | [6 empty] | 2
Slicing UI (fe) - 3 | [8 empty] | 3
Integration response list api (fe) - 1 | [9 empty] | 2
Integration detail response api (fe) - 1 | [8 empty] | 2
Integration push & get command api (fe) - 2 | [9 empty] | 2
Integration blocking soar, close & re-open api (fe) - 1 | [8 empty] | 2
Sprint 3 (25 Maret - 08 April 2026) | 5 | 5 | 5 | 5 | 2 | 2 | 3 | 3 | 4 | 2 | 3 | 2 | 2
Configuration
Create service api configuration list (be) - 1 | [6 empty] | 1
Create service api configuration detail (be) - 1 | [7 empty] | 1
Create service api configuration update & create (be) - 3 | [6 empty] | 2 | 2
Slicing UI (fe) - 2 | [8 empty] | 2
Integration configuration list & detail api (fe) - 1 | [9 empty] | 2
Integration configuration update & create api (fe) - 2 | [8 empty] | 2
Sprint 4 (09 - 20 April 2026) | 5 | 5 | 5 | 5 |  | 2 | 2 | 2 | 2 | 2 | 5 | 2 | 2
UAT / Re-UAT
D2P
Documentation
Total | 20 | 20 | 20 | 20 | 9 | 14 | 17 | 16 | 13 | 8 | 13 | 8 | 8

## Sprint - Mandays (COGS)
Nama Project : WATI CR
Start Date : 18 Februari 2026
Start Date : 20 April 2026
Role | Resources | Grade | Man Rate | Total Mandays | Total COGS
System Analyst | Muhammad Bahtiar |  |  | 20
Technical Leader | Rafi Muhammad Mahrus |  |  | 20
Business Analyst | Deafrin Kirana Senabilla |  |  | 20
Scrum Master | Deafrin Kirana Senabilla |  |  | 20
UI/UX Designer | Inkra Andini Firmansyah |  |  | 9
Database Administrator | Restu Agil Yuli Arjun |  |  | 14
Backend Engineer | Raden Alam Sanjaya |  |  | 17
Backend Engineer | Daffa Radhitya Wina Putra |  |  | 16
Frontend Engineer | Muhammad Rafli |  |  | 13
Frontend Engineer | Atsal Faiz Pramatya |  |  | 8
Quality Assurance | Kayla Chelsea |  |  | 13
DevOps Engineer | Zaky Leo Wardana |  |  | 8
Technical Writer | Stella Priska Palit |  |  | 8
|  |  | Total | 186 | 0