## WBS
Nama Project : AI PDF Extractor & Summarizer with RBAC
Start Date : 2026-04-01
Start Date : 2026-05-26
WBS | April 2026 | [21 empty] | Mei 2026
| Sprint 1: Foundation & RBAC | [9 empty] | Sprint 2: AI Core Development | [9 empty] | Sprint 3: Integration & Admin Dashboard | [9 empty] | Sprint 4: QA & Deployment
Task | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26
Project Initiation
Requirement Gathering & Tech Stack Setup | bar: Sprint 1: Foundation & RBAC 1 to Sprint 1: Foundation & RBAC 2
Database Schema Design (Auth & RBAC) | bar: Sprint 1: Foundation & RBAC 3
Development
Backend - Authentication & RBAC
Implement JWT Auth & Middleware | bar: Sprint 1: Foundation & RBAC 6 to Sprint 1: Foundation & RBAC 7
Role Management System (Admin/User) | bar: Sprint 1: Foundation & RBAC 8 to Sprint 1: Foundation & RBAC 10
Backend - AI Core
PDF Parsing & Text Extraction Service | bar: Sprint 2: AI Core Development 15 to Sprint 2: AI Core Development 17
AI Integration (LLM Prompting for Summary) | bar: Sprint 2: AI Core Development 20 to Sprint 2: AI Core Development 22
File Storage Management (S3/Minio) | bar: Sprint 2: AI Core Development 23 to Sprint 2: AI Core Development 24
Frontend - UI Implementation
Dashboard & PDF Upload Interface | bar: Sprint 2: AI Core Development 27 to Sprint 3: Integration & Admin Dashboard 30
Admin Panel: User & Activity Monitoring | bar: Sprint 3: Integration & Admin Dashboard 1 to Sprint 3: Integration & Admin Dashboard 6
Result Visualization (Summary View) | bar: Sprint 1: Foundation & RBAC 7 to Sprint 1: Foundation & RBAC 8
Testing & Finalization
Integration Testing (AI + Auth) | bar: Sprint 3: Integration & Admin Dashboard 11 to Sprint 4: QA & Deployment 13
UAT & Bug Fixing | bar: Sprint 4: QA & Deployment 14 to Sprint 4: QA & Deployment 19
Production Deployment (Docker/K8s) | bar: Sprint 4: QA & Deployment 20 to Sprint 4: QA & Deployment 22
Final Documentation | bar: Sprint 4: QA & Deployment 25 to Sprint 4: QA & Deployment 26